# TECHNICAL EDUCATION QUALITY IMPROVEMENT PROGRAMME (PHASE - III)

**Equity Action Plan Dec 2020 to March 2021 by 20th November 2020**

**Name of Institute: Government College of Engineering, Jalgaon, Maharashtra**

**Part A : For soft activities**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.**  **No.** | **Activity** | **Action to be taken** | **Coordinator from the Institute** | **Executing agency** | **Date &duration** | **Frequency** | **Whether continuing from last action plan or new activity** | **Indicator to measure outcome (should be quantifiable)** | **Estimated Expenditure (Lac.)** | **Sustainability Plan (Whether the activity will be conducted after the completion of the project Yes/No)** | **If yes, what will be the source of funding** |
| **1.** | Mentoring | Faculty Mentor | All Faculty (25 students per faculty) | Concerned Faculty | Continuous | 2 meeting per semester | Yes | Grievances address satisfactory  Academic | 1.00 | Yes | TEQIP Four Fund |
|  |  |  |  |  |  |  |  | progress |  |  |  |
| **2.** | Academic Support | Remedial classes | Faculty- First Year | In house | Second week of September and March every year | Diagnostics test at beginning of each semester, and remedial classes continuously  thereafter | Yes | To enhance passing % of relevant courses | 20.00 | Yes | TEQIP Four Fund |
| **3.** | Upgrade the knowledge of teacher | Deputation to enroll QIP/part time PhD, Conferences, seminar, participate in  R& D activity | Nodal Officer Faculty Development | Concerned organization | Continuous | ongoing | Yes | Increase in %of teachers enrolled for Ph.D.  No. of Publications | 5.00 | NO | -- |
| **4.** | Social Friendly atmospheres | Adequate and suitable facility for women students and  faculty,transgender | In-charge- Women grievances cell | In house | Continuous | ongoing | Yes | No. of beneficiaries | 2.00 | Yes | TEQIP Four Fund |

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **5.** | Facility for physically challenged students | Creation of facility for physically challenged  Students.  Renovation of toilet blocks. | I/C Building works committee | In house | Continuous | ongoing | Yes | Increased no of disabled students | 1.00 | Yes | TEQIP Four Fund |
| **6.** | Language Competency | Set up of  language laboratory | I/C Language Lab | In house | Continuous | ongoing | Yes | Increase in %of  spoken English students | 1.00 | Yes | TEQIP Four Fund |
| **7.** | Internship / Placement | Training, internship and placement of  weak students | Dean III &TPO | Industry, Alumni | Continuous | ongoing | Yes | Number of students with placements | 5.00 | NO | - |
| **8.** | Address need of Women students | To set up intuitional mechanism to protect and address need of Women students | In-charge Women grievances cell | In house | Continuous | ongoing | Yes | No. of beneficiaries | 1.00 | Yes | TEQIP Four Fund |

Note:

1. For suggestive activity please prefer column1of table of details of Equity Action plan in section8 of Project Implementation Plan(PIP)
2. If the activities are being carried out by the outside agency, mention name of the agency
3. Same activity if repeated should be mentioned in a new row
4. While specifying the indicator please refer column5 “monitoring Indicators” table of details of Equity Action plan in section8 of Project Implementation Plan(PIP)